## Sheet1
Action | EKS on EC2 | EKS on Fargate (Exception)
What's New / Breaking in 1.35 ("Timbernetes") In-Place Pod Resource Updates — adjust CPU/memory without restarting the pod --pod-infra-container-image kubelet flag removed — custom AMIs relying on it need updating IPVS mode in kube-proxy deprecated — ahead of full removal in 1.36; plan the migration off IPVS now
Pre-Flight Checks
Read Release notes: https://github.com/kubernetes/kubernetes/blob/master/CHANGELOG/CHANGELOG-1.35.md#v1350 https://docs.aws.amazon.com/eks/latest/userguide/kubernetes-versions-standard.html#kubernetes-1-35 | Note applicable changes
Scan for deprecated API usage | pluto detect-files -d gitops/ \ --target-versions k8s=v1.35.0 # or kubent # or, directly against the live API server kubectl get --raw /metrics ¦ grep apiserver_requested_deprecated_apis | New API versions may likely have new file structure, use the built-in kubectl-convert plugin to automatically rewrite manifest schemas to the target version: # Install via package manager, then run: kubectl convert -f old-hpa.yaml --output-version autoscaling/v2 > new-hpa.yaml
Check add-on compatibility — VPC CNI, CoreDNS, kube-proxy, EBS/EFS CSI driver, ALB controller | aws eks describe-addon-versions \ --addon-name vpc-cni \ --kubernetes-version 1.35 \ --query "addons[].addonVersions[].{Version:addonVersion,Default:compatibilities[0].defaultVersion}" \ --output table # repeat for each add-on you run for addon in vpc-cni kube-proxy coredns eks-pod-identity-agent aws-ebs-csi-driver; do echo "=== $addon ===" aws eks describe-addon-versions \ --addon-name $addon \ --kubernetes-version 1.35 \ --query "addons[].addonVersions[?compatibilities[0].defaultVersion==\`true\`].addonVersion" \ --output text done
Check what's currently installed: | aws eks describe-addon \ --cluster-name <cluster-name> \ --addon-name vpc-cni \ --query "addon.addonVersion"
Run AWS's built-in upgrade insights — catches incompatibilities automatically: | Run AWS's built-in upgrade insights — catches incompatibilities automatically:
Third-Party Controller Compatibility
Check current versions: | helm list -A kubectl get deployment -n argocd argocd-server -o jsonpath='{.spec.template.spec.containers[0].image}' kubectl get deployment -n kube-system aws-load-balancer-controller -o jsonpath='{.spec.template.spec.containers[0].image}' kubectl get deployment -n external-secrets external-secrets -o jsonpath='{.spec.template.spec.containers[0].image}' kubectl get deployment -n ack-system -o jsonpath='{range .items[*]}{.metadata.name}{"\t"}{.spec.template.spec.containers[0].image}{"\n"}{end}' kubectl get deployment -n monitoring grafana -o jsonpath='{.spec.template.spec.containers[0].image}' kubectl get deployment -n keda keda-operator -o jsonpath='{.spec.template.spec.containers[0].image}'
Cross-check against each project's compatibility docs before bumping the control plane: (Upgrade order: AWS Load Balancer Controller in the same window as the control plane — It is a node/traffic-critical, so treat like Stage 5's add-ons) | ArgoCD — https://argo-cd.readthedocs.io/en/stable/operator-manual/tested-kubernetes-versions/ AWS Load Balancer Controller — release notes on the aws-load-balancer-controller GitHub releases page External Secrets Operator — https://external-secrets.io/latest/introduction/stability-support/ Grafana Operator - https://github.com/grafana/grafana-operator/releases ACK - https://aws-controllers-k8s.github.io/docs/services ACK Lambda - https://github.com/aws-controllers-k8s/lambda-controller/releases ACK SQS - https://github.com/aws-controllers-k8s/sqs-controller/releases ACK SNS - https://github.com/aws-controllers-k8s/sns-controller/releases KEDA - https://github.com/kedacore/keda/releases
Backup
Cluster objects (Deployments, Services, ConfigMaps, Secrets, CRDs, RBAC) with Velero | velero backup create pre-upgrade-1.35 --include-namespaces='*' --wait Verify restore capability (Critical) velero restore create --from-backup pre-upgrade-1.35 EKS's control plane etcd is managed by AWS — there's no self-service snapshot/restore for it. If a control-plane upgrade goes wrong, the realistic recovery path is restoring workloads onto a new cluster from the Velero backup, not an etcd rollback. | Comfirm possibility
Control Plane Upgrade - ekctl |  | N/A Fargate in use
Node Group/Fargate Profile Upgrade |  | bump 1.34 > 1.35 Verify kubectl get nodes -o wide # confirm all nodes report the target version
Add-on Upgrade |  | Upgrade and Verify Add-ons
Post-Upgrade Validation | kubectl get nodes -o wide # confirm every node reports the target version kubectl get pods -A --field-selector=status.phase!=Running # catch CrashLoopBackOff or Pending workloads early aws eks list-insights --cluster-name <cluster-name> # re-check for new warnings post-upgrade terraform plan # should show zero diff — confirms actual state = desired state
Rollback Strategy | Rollback is a per-layer decision, not a single switch — each layer has a different (or nonexistent) rollback path. Triage first, then match the fix to the layer.
Triage: find which layer broke | kubectl get nodes -o wide kubectl get pods -A --field-selector=status.phase!=Running kubectl get events -A --sort-by='.lastTimestamp' ¦ tail -50 aws eks describe-cluster --name <cluster> --query "cluster.{status:status,health:health}" aws eks list-insights --cluster-name <cluster> kubectl logs -n kube-system <addon-pod> --previous # if an addon pod is crashlooping
Know your rollback constraints per layer | Layer ¦ Can you roll back? Control plane version: No. EKS has no self-service downgrade. This layer is fix-forward only. Node groups: Yes — blue/green swap back to a node group pinned to the old AMI/version Add-ons: Yes — pin addon_version back to the previous known-good version via Terraform Your workloads/manifests: Yes — revert via Git/GitOps, independent of cluster version
Fix by scenario | Control plane issue (API server misbehaving, admission webhook failures): No downgrade path exists. Fix forward — patch the offending config/webhook, open an AWS Support case if it looks like an AWS-side regression, or, for severe unfixable breakage, stand up a new cluster on the old version and migrate workloads back via Velero restore + GitOps redeploy.
Node/kubelet issue (e.g. a custom AMI broke because of a removed kubelet flag): |  | Temporarily roll back to a fargate profile on the previous version Roll traffic back to the old-version fargate profile
Add-on issue (e.g. VPC CNI networking broke, CoreDNS resolution failing): |  | Verify action approach (reinstall or otherwise)
Workload issue (e.g. a Deployment breaks because it used a Kubernetes API version removed in the new release) | Fix forward only — the control plane isn't coming back down, so update the manifest to the current API version and redeploy via GitOps.
General incident sequence | Stabilize first, diagnose second — scale/reroute/rollback the workload layer immediately if something's down; that's always possible regardless of cluster version. 1. Isolate the layer using Step 1's triage. 2. Check whether a same-layer rollback exists (nodes/add-ons: yes; control plane: no). 3. If rollback is available and fast — do that first to restore service, then investigate root cause out of the hot path. 4. If rollback isn't available (control plane) — fix forward under pressure, or fall back to the Velero-restore-onto-new-cluster path for severe cases. 5. Re-validate using the Post-Upgrade Validation checklist above. 6. Postmortem — feed whatever broke back into Pre-Flight Checks so it's caught before the next upgrade, not after.
EKS Version Rollback | https://aws.amazon.com/blogs/aws/upgrade-amazon-eks-clusters-with-confidence-using-kubernetes-version-rollbacks/
This feature provides a 7-day window to reverse the control plane upgrade back to previous version
Communication Plan | Inform all stake holders before commencement, share the upgrade plan/steps/rollback